## Standards
QID | Standard | QuestionNumber | Stage | StandardType
Pro/1.01 | Create a project charter, with minimum data per the Project Charter Template | 1 | Propose | Project
Pro/1.02 | If seed funding is required, submit the Project Charter with completed seed funding details to the appropriate governance forum for approval. Tier 1s see Project Stage Gate Checklist | 2 | Propose | Project
Pro/1.03 | Architecture Spec - Vision​ completed and approved by technical governance bodies | 3 | Propose | Project
Pro/2.01 | Develop a Business Case for approval by internal and central governance, per Business Case – minimum data. Tier 1s use the Project Finance Evaluation Tool | 1 | Discover | Project
Pro/2.02 | Capture, prioritise and obtain approval of sufficient requirements to set the scope boundaries for the initiative, to enable forecasting and to inform the design process, per the SDLC Minimum Control Standards for Solution Requirements. | 2 | Discover | Project
Pro/2.03 | Document financial, non-financial and risk reduction benefits for inclusion in the Business Case. | 3 | Discover | Project
Pro/2.04 | Conduct an assessment of delivery risk (via RAID Register) and delivered risk (via Delivered Risk Traceability) | 4 | Discover | Project
Pro/2.05 | Document the risk profile (including owned and timebound mitigations) and integrated assurance approach in the Business Case | 5 | Discover | Project
Pro/2.06 | ​Architecture Spec - Blueprint​ completed and approved by technical governance bodies | 6 | Discover | Project
Pro/2.07 | Service Impact Assessment​ completed, with reference to the Service Introduction homepage​ | 7 | Discover | Project
Pro/2.08 | Global Privacy Impact Assessment​ completed and consultation with the Global Privacy Council, via the Group Privacy Officer. | 8 | Discover | Project
Pro/2.09 | Conduct an assessment against the Tiering Assessment Criteria to identify governance required | 9 | Discover | Project
Pro/2.11 | Undergo the stage gate review associated with Business Case approval, Tier 1s see Project Stage Gate Checklist. | 11 | Discover | Project
Pro/3.01 | ​Set-up a document repository to ensure documentation is stored centrally, maintained and available as evidence | 1 | Design & Deliver | Project
Pro/3.02 | Tier 1s create drawdown requests for incremental funding, per Funding Drawdown Request - minimum data​. Note: Initiatives may be granted funding in stages with a 6 month maximum planned scope delivery | 2 | Design & Deliver | Project
Pro/3.03 | Create a refreshed Business Case when seeking materially changed funding (+10% to costs, -10% to financial benefits or risk reduction benefits no longer achievable). | 3 | Design & Deliver | Project
Pro/3.04 | Undergo the stage gate review associated with Funding Drawdown, Tier 1s see Project Stage Gate Checklist. | 4 | Design & Deliver | Project
Pro/3.05 | Engage functional areas and BAU recipients of project-initiated change to ensure business readiness, including Risk and Control owners to update RCSAs (Risk and Control Self-Assessments) and track through operating effectiveness | 5 | Design & Deliver | Project
Pro/3.06 | Detailed requirements to be captured, approved and traceable from high level requirements to testing completion, per the SDLC Minimum Control Standards for Solution Requirements. | 6 | Design & Deliver | Project
Pro/3.07 | Solution decision to be made based on an assessment of options with regard to their viability, maintainability and the requirements, per the SDLC Minimum Control Standards for Solution Decision and Assessment | 7 | Design & Deliver | Project
Pro/3.08 | Solution Architecture to be documented and submitted for review by the relevant Divisional or Global review forums as required, per the SDLC Minimum Control Standards​ for Solution Architecture and Design | 8 | Design & Deliver | Project
Pro/3.09 | Relevant solution components to be developed in accordance with detailed designs following development methods and documentation standards, and quality assurance (QA) and approval requirements, per the SDLC Minimum Control Standards​ for Solution Build | 9 | Design & Deliver | Project
Pro/3.1 | Test strategy/plan and requirements traceability to be captured; and testing and defect management to be performed, per the SDLC Minimum Control Standards for Test Strategy and Requirements Traceability; and Testing and Defect Management | 10 | Design & Deliver | Project
Pro/3.11 | Service Introduction Checklist​​ completed prior to solution release, with reference to the Service Introduction homepage​ | 11 | Design & Deliver | Project
Pro/3.12 | An implementation plan, approved by the relevant stakeholders, to be followed, per the SDLC Minimum Control Standards​ for Implementation. | 12 | Design & Deliver | Project
Pro/3.15 | Undergo the stage gate review associated with Solution Release, Tier 1s see Project Stage Gate Checklist | 15 | Design & Deliver | Project
Pro/4.01 | End of Warranty Acceptance received from Sponsor | 1 | Embed & Evolve | Project
Pro/4.02 | Handover the Benefits Register to benefit owners for tracking and reporting benefits realisation | 2 | Embed & Evolve | Project
Pro/4.03 | Close out all temporary initiative related elements created to facilitate delivery | 3 | Embed & Evolve | Project
Pro/4.04 | Business Owners engage Finance in the execution of the financial benefits realisation | 4 | Embed & Evolve | Project
Pro/4.05 | Capture lessons learned, with minimum data per the Lessons Learned Template​ and conduct a Post Implementation Review. For IT delivery, per the SDLC Minimum Control Standards​​​ for Post Implementation Review | 5 | Embed & Evolve | Project
Pro/4.07 | Undergo the stage gate review associated with Project Closure, Tier 1s see Project Stage Gate Checklist | 7 | Embed & Evolve | Project
Pro/5.01 | Track and report on initiative progress as defined by reporting cycles, see Project Status Reporting – minimum data | 1 | Project Management | Project
Pro/5.02 | Actively manage Risks, Assumptions, Issues and Dependencies, maintaining a register, with minimum data per the RAID Register Template | 2 | Project Management | Project
Pro/5.03 | Develop, maintain and regularly report against an approved timeline, per the Agile Board/Project Schedule – minimum data | 3 | Project Management | Project
Pro/5.04 | Impact of changes to be understood, tracked and approved, via a change control process, including the maintenance of a change register​, per the Change Request Register – minimum data | 4 | Project Management | Project
Pro/5.05 | Ensure adherence to the QBE Global Change Management Framework | 5 | Project Management | Project
Pro/6.01 | Governance forums adhere to a Terms of Reference document, with minimum data per the Terms of Reference for Governance Forums Template | 1 | Project Governance | Project
Pro/6.02 | Ensure Sponsors and Steering Committee members understand roles and responsibilities | 2 | Project Governance | Project
Pro/7.01 | Maintain an up to date Financial tracker, available for review by Finance and PMOs, per Initiative Financial Tracker – minimum data | 1 | Financial / Benefits | Project
Pro/7.02 | Follow month-end financial management and reporting processes | 2 | Financial / Benefits | Project
Pro/7.03 | Develop, maintain and regularly report against the Benefits Register | 3 | Financial / Benefits | Project
Pro/7.04 | Assess risk to benefits realisation. Any material change to estimated benefits (-10% to financial benefits, non-financial or risk reduction benefit not achievable) are subject to change control for approval by the governance forum that approved funding.​ | 4 | Financial / Benefits | Project
Pro/1.04 | Define the change story and identify your stakeholders. Determine the high-level Change Management budget required | 4 | Propose | Project
Pro/2.1 | Understand and document the change strategy to ensure successful delivery against defined success measures | 10 | Discover | Project
Pro/3.13 | Deliver the Change Management Strategy. Future state plans are enacted for impacted areas | 13 | Design & Deliver | Project
Pro/3.14 | Communication / Training / and business readiness activities have been completed as planned. Remediation activity undertaken as necessary | 14 | Design & Deliver | Project
Pro/4.06 | Develop a post implementation approach that allows business to embed and sustain the change | 6 | Embed & Evolve | Project
Por/7.01 | All initiatives have a documented Terms of Reference for governance forums that has been approved by the PMO as meeting the minimum data requirements. | 1 | Governance | Portfolio
Por/7.02 | All initiatives maintain a robust Risk Profile​ with mitigation strategies that are timebound, owned and budgeted. Note: this will be a key input into initiative assurance activity. | 2 | Governance | Portfolio
Por/7.03 | Any exceptions to compliance against Project and Portfolio Minimum Standards are agreed by central governance. | 3 | Governance | Portfolio
Por/7.04 | Ensure that Business Cases are of high quality, meet the Business Case – minimum data, are subject to the Business Case Panel Review process and that there is a single accountable sponsor.​ | 4 | Governance | Portfolio
Por/7.05 | Maintain a central register of approvals for provision of seed funding, Business Case approval and funding drawdown across the portfolio. | 5 | Governance | Portfolio
Por/7.06 | Record approved Business Case data, which constitutes a formal baseline for performance and change measurement.​ | 6 | Governance | Portfolio
Por/7.01 | Total cost of prioritised initiatives stays below the upper limit of the total approved for the portfolio. Any overallocation driven by excess demand is presented to governance for approval. | 1 | Prioritisation | Portfolio
Por/7.02 | All initiatives seeking prioritisation provide a standardised set of data points, per Prioritisation – minimum data. | 2 | Prioritisation | Portfolio
Por/7.01 | Manage the overall initiative pipeline/ demand and investment allocation to mitigate risk of portfolio overspend and ensure strategic allocation of capital. | 1 | Funding | Portfolio
Por/7.02 | Ensure Tier 1 initiatives use the Project Finance Evaluation Tool to generate Business Case financial and benefit data.​ | 2 | Funding | Portfolio
Por/7.03 | Ensure that the delivery of work scoped within the Business Case only begins after formal approval. | 3 | Funding | Portfolio
Por/7.04 | In the instance of material deviations (+/-10%) to approved costs/ benefits, ensure there is a formal re-assessment via change control (for approval via Steering Committee and PMO) and re-baselining of Business Case data. | 4 | Funding | Portfolio
Por/7.05 | Ensure funding drawdown requests are performed within approved limits and for initiatives spending >1 year in execution or delivering across multiple financial years, that funding is granted in stages based on scope delivery. | 5 | Funding | Portfolio
Por/7.01 | Ensure all initiatives adhere to the Three Lines of Defence model, per the Line 2 Project Risk Management Guidelines. ​ | 1 | Assurance | Portfolio
Por/7.02 | Take a risk-based approach to ensure significant and/or complex initiatives have appropriate assurance oversight including a budgeted, documented assurance plan supported by the relevant PMO, Risk, Compliance, Regulatory and Internal Audit team | 2 | Assurance | Portfolio
Por/7.03 | Review initiatives to ensure compliance to minimum standards and for delivery quality assurance. | 3 | Assurance | Portfolio
Por/7.04 | Perform formal stage gate reviews where required. For Tier 1s see Project Stage Gate Checklist. | 4 | Assurance | Portfolio
Por/7.01 | PMOs use data submitted from initiatives to produce aggregated dashboards and consolidated status reporting to an agreed schedule and in support of EPMO. | 1 | Reporting & Insights | Portfolio
Por/7.02 | Portfolio managers maintain and update (minimum quarterly) a central Benefits Register, for all initiatives within the portfolio, per Portfolio Benefits Tracker - minimum data. | 2 | Reporting & Insights | Portfolio
Por/7.03 | PMOs overseeing Tier 1 initiatives ensure completion of monthly Project Status Reports to enable aggregate tracking of the major QBE programs including up to Group Board Operations & Technology Sub-Committee. | 3 | Reporting & Insights | Portfolio
Por/7.04 | The health of the portfolio is monitored over time across key delivery areas (for example, risk, issues, aggregate change impacts, dependency management, overall cost and forecasting) to enable proactive reporting and intervention.​ | 4 | Reporting & Insights | Portfolio

## Categories
Title | ItemType
AUSPAC | Portfolio
BB UW&P | Portfolio
EO | Portfolio
Cyber | Portfolio
NA | Portfolio
BB Claims | Portfolio
IT Transformation | Portfolio
Group | Portfolio
DPMO - EO | Project
DPMO - NAO | Project
DPMO - AUSPAC | Project
Group HR | Project
Group Finance | Project
GSSC | Project
RISKsight | Tier 1 Programme
Insights | Tier 1 Programme
Optimum | Tier 1 Programme
BB UW&P | Tier 1 Programme
Majesco | Tier 1 Programme
Cyber | Tier 1 Programme
BB Claims | Tier 1 Programme
MtM | Tier 1 Programme
FTP | Tier 1 Programme
Strategic Pricing | Tier 1 Programme